## Slide 1: Project Status Overview
AREA | SUMMARY
Budget | Unallocated $142,282 budget of $611,520
Technology | Leaderboards not yet developed
People | 5 of 5 hired employees are still alive and working / on track
Schedule | Required features/systems are 4 weeks and 3 days behind schedule
Logistics | In-studio / on track

## Slide 2: What & Why
AREA | ASK | JUSTIFICATION | IMPACT
Budget | None | We still have $142,282 of unallocated budget remaining | N/A
Technology | Cut optional Leaderboards | Demonstrated to be of low priority as of Development and Quality Directors Report | Ensures other features are able to be properly implemented and tested
People | Hire 1x contract general programmer | Regain ground on implementing features, relieve work load on team | Ease load on team due to delays from playtesting
Schedule | Remove planned demo events | 4 weeks and 3 days behind schedule and do not want to show incomplete game that may hurt sales | Allows for more time for the full team to work on the game project
Logistics | Additional workspace for contract general programmer | Currently our space is for 5 people, but bringing a contract worker will require more workspace | The team can connect with the contract worker and bring them up to speed and aids in communication

## Slide 3: Mitigation Plan
AREA | ASK | IMPROVES
Budget | None | N/A
Technology | Cut optional Leaderboards | Required systems development time and ensures that they are properly tested before launch
People | Hire 1x contract general programmer | Team morale by reducing the current feature load on the team and avoids crunch
Schedule | Remove planned demo events | Team morale by avoiding crunch before demo event and allows for the full team to continue to work on the game without time loss
Logistics | Additional workspace for contract general programmer | Team morale and communication between new contract worker and the rest of the team as a whole.