## Status Report Template
Overview |  | Code Name: Project Nautilus | Working Title: Conch-Fish-Scate | Game Genre: Arcade | Project Lead: Travis Moore
Area/Status | Summary | For Wheel of Reality Event #3 I was given the Tech Event which states: "The level design for a specific level or game mode is not as strong as you would like and initial feedback from internal company playtests seems to support this assessment". In order to mitigate this setback and remain within our Holiday 2017 I have proposed two solutions to mitigate this risk. The first mitigation involves cutting the leaderboards feature that has recently been approved as an optional feature. By cutting this feature we free up a month of planned development time that can instead be used to redesign the level/game mode. Another proposed solution is to hire a senior-level Level designer for three weeks time in order to tackle this problem. This would allow us to keep on track with the holiday release without cutting the leaderboards. This solution also has the added benefit of providing us with another individual's expertise in solving this kind of problem, a potential risk mitigation from our Gameplay & UX/UI Designer and General Programmer not having the experience or knowledge for designing strong levels that led to this problem in the first place. While the second solution costs more budget, we have enough unallocated budget to accomodate for the second proposed solution without needing to sacrifice the optional leaderboards.
Scope | Level design/game mode is not strong (playtests report)
Budget | Could cost time/budget to redesign levels/game mode
People/Resources | Level designers / gameplay programmers
Risks/Issues | Level design/game mode is not strong (playtests report)
Milestones | Achievements are required, Leaderboards are optional.
Action Items | On track
Scope Change | Date | Approved? | Description
Initial Scope | Month 1 | Yes | iPhone Arcade Game
Level Design | Month 6 | No | Level design/game mode is not strong (playtest reports)
Level/Game mode Redesign | Month 6 | No | Proposal to cut optional leaderboards to focus personel on redesigning level/game mode to a higher quality or hire contract level designer to work on level design while hired personnel redesign gamemode.
Budget | Original | Baseline | Forecast | Notes
Staff | 447200 | 453460 | 453460 | Additional $6,360 for a three week contract senior-level Level Designer at $53/hour
Engine Licences | 4932 | 5057 | 5057 | 1 month of Unity3D Pro ($125/month) for the contract Level Designer
Software Licences | 1288.9 | 1288.9 | 1288.9
Device Costs | 2507.65 | 2507.65 | 2507.65
Other Costs | 108.5 | 108.5 | 108.5
Unallocated | 155482.95 | 148997.95 | 148997.95 | $6,485 budget taken from unallocated to accommodate contract Level designer and additional Unity3D Pro license
Total | 611520 | 611520 | 611520
People/Resource | Date | Mitigation | Notes
Cut Leaderboards | Month 6 | Frees up time/personnel to work on improving level design/game mode | Cutting leaderboards was approved in WoR 2
Hire senior-level contract Level Designer | Month 6 | Provides expertise in level redesign and frees up time/personnel to improve game mode
Risk/Issue | Type | Created | Mitigation Plan | Mitigation Date
Slow Internet | Risk | Month 3 | Investigate reason for slowdown. Severed fiber optic cable repaired. | Month 4
Scope | Risk | Month 4 | Achievements are required, but Leaderboards are optional | Month 5
Level design/game mode | Risk | Month 6 | Propose either: a) cut leaderboards feature to free up time/personnel to work on level design/game mode or b) hire contract level designer to work on level design to free up time/personnel to work on game mode
Milestone | Baseline Date | Current Date | Notes
(Required )Monetization Plan | Month 3 | Done
(Required) Timed Mode | Month 4 | Done
(Required) Game Save | Month 6 | Month 7 | Designed, not implemented.
(Required) Account Management | Month 7 | Month 8 | Planned.
Achievements | Month 9 | Month 10 | Planned.
(Optional) Leaderboards | Month 9 | Month 10 | Potentially Cut
Action Item | Assigned To | Created | Due
Hire contract senior-level Level Designer | Travis Moore | Month 6 | TBD (awaiting approval)
Level Redesign | Gameplay & UX/UI Designer | Month 6 | Month 7
Game mode redesign | General Programmer | Month 6 | Month 7
Level / game mode playtesting | Gameplay & UX/UI Designer | Month 6 | Month 7