## Sample Status Report
Overview
Area/Status | Summary
Scope | Voice Acting support
Budget | Font pricing unexpectedly high
Resources | Sound engineering experience
Risks/Issues | Fan art contest for user generated content
Milestones | Game mode 2 late, slip or reduce scope.
Action Items | On track
Scope Change | Date | Approved? | Description
Initial Scope | 2016-01-04 | Y | Mobile game
Voice Actors | 2016-02-23 | N | Changes to support voice acting. Script, implementation, timing, volume tuning, etc.
Marketing Assets | 2016-02-23 | N | Proposal to use in game assets for marketing materials, e.g., on buses. Will need to be customized.
Budget | Original | Baseline | Forecast | Notes
Staff | 447200 | 455200 | 455200 | $8000 for two week contractor
Licensing | 14000 | 14000 | 24000 | $10,000 for font licensing
Test Devices | 3000 | 3000 | 3000
Voice Acting | 0 | 0 | 6000 | Proposal for added scope
Unallocated | 35000 | 27000 | 11000 | Buffer almost gone with 6 months left.
Total | 499200 | 499200 | 499200
People Resource topic | Date | Mitigation | Notes
Expert contractor | 2016-02-23 | This removes risk
Pat on leave for 2 weeks in March | 2016-03-01 | Already in estimates
Sound Engineering | 2016-02-23 | Voice acting mixing by jr sound engineer
Risk/Issue | Type | Created | Mitigation Plan | Mitigation Date
Voice Actor contract | Issue | 2016-02-23 | Once agreement signed, only use professional voice actors | 2016-03-01
Asset server hardware upgrade | Risk | 2016-02-14 | Downtime projected, 2-5 days. | 2016-03-01
Fan art contest | Risk | 2016-02-23 | Proposal to incorporate fan art in game. Delay contest until launch to mitigate | 2016-02-23
Bus art | Risk | 2016-02-23 | Delay bus art advertising until launch as well | 2016-02-23
Milestone | Baseline Date | Current Date | Notes
Monetization Plan | Month 3 | Done
Play Mode 1 | Month 4 | Done
Play Mode 2 | Month 6 | Month 7 | Code complete, in testing.
Game Save | Month 6 | Month 7 | Designed, not implemented.
Account Management | Month 7 | Month 8 | Planned.
Achievements | Month 9 | Month 10 | Planned.
Leaderboards | Month 9 | Month 10 | Could cut.
Action Item | Assigned To | Created | Due
Bus assets proposal review | Iron man | 2016-02-09 | Done
Fan art contest proposal review | Storm | 2016-02-09 | Done
Investigate cheaper fonts | Dead Pool | 2016-02-23 | 2016-03-09
Sign expert contractor | Colossus | 2016-02-16 | Done
Hire voice over staff | Buffy | 2016-02-23 | TBD
Create VO schedule, estimates | Buffy | 2016-02-23 | TBD

## Status Report Template
Overview |  |  | Project
Area/Status | Summary
Scope
Budget
People/Resources
Risks/Issues
Milestones
Action Items
Scope Change | Date | Approved? | Description
Achievements are still required but Leaderboards are now optional | Month 4 | Yes | See WoR #2 Month 4
Budget | Original | Baseline | Forecast | Notes
Staff | 447200 |  |  | 5 people total: Project Manager (Mid), General Programmer (Senior), Gameplay & UX/UI Designer (Mid), 2D Artist (Junior), QA (Junior)
Engine Licences | 4932 |  |  | 3x Unity 3D
Software Licences | 1289 |  |  | 1x Adobe Creative Cloud
Device Costs | 2508 |  |  | 1x iPhone 7 iOS 10.x (premiere experience) and 1x iPhone 6 iOS 9.x
Other Costs | 609 |  |  | Apple iOS Store costs, (WoR #4) Noise cancelling headphones
Contract Workers | 12700 |  |  | (WoR #3) Month 6 - 6 week contract level designer.
Unallocated | 142282
Total Budget | 611520
People/Resource | Date | Mitigation | Notes
Contract Level Designer | (WoR #3) Month 6 | $12,700 for 6 weeks of contract level designer.
Engineering | (WoR #4) Month 7 | Purchased $500 noise cancelling headphones, 3 day slowdown of effort by engineer until headphones acquired.
Risk/Issue | Type | Created | Mitigation Plan | Mitigation Date
Internet access is too small and is causing performance issues | Logistics | (WoR #1) Month 2 | The slowed internet pipe/connection was caused by a severed regional fiber optic cable near Reality Games. The cable is repaired with no lasing impact.
Development and Quality Directors have determined that the value and estimated costs for your game project have changed. | Logistics | (WoR #2) Month 4 | Achievements are still required and Leaderboards are now optional.
Level design/game mode is not strong (playtest report) | Tech | (WoR #3) Month 6 | 3 week delay for redesign, implementation, and testing. $12,700 for 6 weeks of contract level designer. Managing a contractor will impact the project lead's time.
Engineer is having problems with the noise in the studio | Logistics | (WoR #4) Month 7 | Purchased $500 noise cancelling headphones, 3 day slowdown of effort by engineer until headphones acquired.
Playtesting shows that the tutorial is not working and that it might need new supporting tech to expand it. | Tech | (WoR #5) Month 8 | The team reworks the the issues causing player confusion and is it clear that the game mechanic is fine, just the wording/presentation caused issues. 1 week delay for the player interviews and revisions.
No understanding of what players are doing, their play patterns, or how to convert them to a paying user. | Logistics | (WoR #6) Month 9 | Working with a data analyst you discover what is needed but lose 1 week of effort for engineering, design, QA, and production (art is not impacted) on research, implementation, testing, and verification. Once implemented you are able to work faster with refinement on the game design and mechanics
Milestone | Baseline Date | Current Date | Notes
Monetization Plan | Month 3
Timed Mode | Month 4
Game Save | Month 5
Account Management | Month 6
Achievements | Month 7
(Optional) Leaderboards | Month 8
Action Item | Assigned To | Created | Due